## Sheet1
HRD Programme FY2013-14 Activity Based Budget
Project Title:
Implementer:
Activity No. | Activity | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Totals
1.1.1 Data collection and baseline survey training (5 days) |  | July: 1175 | 1175
1.1.2 Data collection and baseline field survey (5 days) |  | Aug: 7130 | 7130
1.1.3 Reporting |  | Sept: 720 | 720
1.2.1 5 Training Workshops |  | Nov: 7110 | 7110
0
0
0
0
Total Activity Costs by Month |  | 0 | 1175 | 7130 | 720 | 0 | 7110 | 0 | 0 | 0 | 16135
2.1 Administration costs
|  | 220 | 220 | 220 | 220 | 220 | 220 | 0 | 0 | 0 | 1320
TOTAL COSTS : |  | 220 | 1395 | 7350 | 940 | 220 | 7330 | 0 | 0 | 0 | 17455
PLEASE SEE BELOW FOR FULL BREAKDOWN OF BUDGET.
1.1 | Data collection and analysis | [9 empty] | 9025
1.1.1 | Data collection and baseline survey training to research teams 5 days
| 1. Venue Hire (5 days x £20 per day) | July: 100
| 2. Trainer Fee (£5 days x £100 per day) | July: 500
| 3. Transportation costs - bus (£5 x 10 x 5 days) | July: 250
| 4. Refreshments - tea, coffee, lunch (£5 x 10 participants x 5 days) | July: 250
| 6. Stationery (paper, pens, flipchart paper) | July: 50
| 7. Photocopying (£5 days x £5 per day) | July: 25
| Sub Total 1.1.1 | July: 1175
1.1.2 | Data collection, baseline field survey (5 days)
| 1. Travel costs - car hire (5 days x 1 car x £100 per day) | Aug: 500
| 2. Food costs ( 5 days x £10 x 2 towns x 4 people) | Aug: 400
| 3. Accomodation (5 days x 2 towns x 4 people x £50 per night) | Aug: 2000
| 4. Stationery costs | Aug: 30
| 5. Round table events - Venue Hire £20 per day x 10 days (2 towns) | Aug: 200
| 6. Roundtable events - refreshments (tea / coffee, lunch) £10 per person x 30 x 10 | Aug: 3000
| 7. Facilitator 10 days x £100 | Aug: 1000
| Sub Total : 1.1.2 | Aug: 7130
1.1.3 | Reporting
| 1. Report writing ( facilitator x 2 days x £150) | Sept: 300
| 2. Copy editing | Sept: 150
| 3. Printing (250 copies x £1) | Sept: 250
| 4. Conversion to ebook/ pdf, uploading to website | Sept: 20
| Sub Total 1.1.3 | Sept: 720
1.2 | Training workshops | [9 empty] | 7110
1.2.1 | 5 Training workshops
| 1. Venue hire including equipment hire - projector (5 days x £50) | Nov: 250
| 2. Trainer (£300 per day x 5) | Nov: 1500
| 3. Refreshments (tea, coffee, lunch) x £10 per person x 250 | Nov: 2500
| 4. Travel costs for participants £5 per person x 250 (bus travel) | Nov: 1250
| 5. Travel costs for trainer (Economy Flight UK to Another Country x1) | Nov: 1200
| 6. Accomodation costs for trainer (6 nights x 50 per night) | Nov: 300
| 7. Food costs for trainer - breakfast & dinner (6 days x £10) | Nov: 60
| 8. Stationery (paper, pens, flip chart paper, blu tack) | Nov: 50
| Sub total 1.2.1 | Nov: 7110
| ACTIVITY TOTALS: | [9 empty] | 16135
2.1 | Administration costs
| Project Finance Officer 1 hr x 6 months | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 60
| Project Officer 5hrs per month x 6 months (£12 ph) | 60 | 60 | 60 | 60 | 60 | 60 |  |  |  | 360
| Project Coordinator 10 hrs per month£15 per hour | 150 | 150 | 150 | 150 | 150 | 150 |  |  |  | 900
0
| Total Administration costs | 220 | 220 | 220 | 220 | 220 | 220 |  |  |  | 1320
Example
Example
Example